## Sheet1
Task | Time (Week)
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
Project Planning and Requirement Analysis
Research and Technology Selection
System Design and Architecture
Development Phase 1
Development Phase 2
Testing and Quality Assurance
Deployment Preparation
Deployment and Training
Post-Deployment Support and Optimization